## Budget
HustlePilot
Wedding budget
Free UK wedding budget. All amounts in pounds. Type in the yellow cells.
Your total budget |  | Type your total here, numbers only, for example 15000.
Planned so far | 0
Over or under budget |  | Add your total budget in B5
Item | Planned £ | Actual £ | Paid £ | Left to pay £ | Notes
Venue
Ceremony and register office fees
Catering
Drinks
Photographer
Dress and suit
Flowers
Cake
Music
Stationery
Rings
Hair and make-up
Transport
Favours
Contingency
End of the list. To add an item, insert a row above this line. The totals will count it.
TOTAL | 0 | 0 | 0 | 0
Left to pay is the actual cost (or the planned amount until you have one) minus what you've paid.
Typical UK costs by region, with sources: hustlepilot.app/wedding-costs
Yellow cells are for typing. Green cells work themselves out.
In Excel, formula cells are lightly protected so they don't get overwritten by accident. There's no password: Review > Unprotect Sheet. Google Sheets doesn't keep that protection, but every formula still works.
What's in the full version (Wedding OS Lite UK, £4.99): one file for Excel and Google Sheets. Seven tabs: Home, Setup, Budget, Suppliers, Guests, Timeline, Checklist. Supplier payments update your budget by themselves, and payments due in the next 14 days or overdue are flagged. Room for 50 suppliers and 50 guests. A 50-task starter checklist. Home shows your next 3 actions.
Want the full planner? Wedding OS Lite UK, £4.99: payhip.com/b/iRIuN

## Checklist
HustlePilot
Wedding checklist
Pick the tick in the Done column when a task is finished. Add your own tasks in the empty rows.
When | Task | Done | Notes
12+ months | Agree your total budget
12+ months | Draw up a first guest list
12+ months | Book your venue
12+ months | Choose your ceremony and book the registrar or officiant
12+ months | Book your photographer
9 months | Book your caterer (if the venue doesn't do food)
9 months | Book music for the ceremony and evening
9 months | Choose your dress and suit
9 months | Send save the dates
6 months | Book your florist
6 months | Order your cake
6 months | Book hair and make-up
6 months | Book transport
3 months | Give notice of marriage at your local register office (England and Wales: at least 29 days before)
3 months | Send your invitations
3 months | Buy your rings
1 month | Chase RSVPs and confirm numbers
1 month | Final dress and suit fittings
1 month | Confirm timings with every supplier
1 month | Pay final balances due before the day
Week before | Give final numbers to the venue and caterer
Week before | Pack for the day and the night after
Week before | Hand the rings to whoever looks after them on the day
End of the checklist. To add a task, insert a row above this line.
Tasks | 23
Done | 0
% done | 0%
Yellow cells are for typing. Green cells work themselves out.
In Excel, formula cells are lightly protected so they don't get overwritten by accident. There's no password: Review > Unprotect Sheet. Google Sheets doesn't keep that protection, but every formula still works.
Want the full planner? Wedding OS Lite UK, £4.99: payhip.com/b/iRIuN